## Master_BOM
2-ACRE MORINGA DRIP IRRIGATION PROJECT — MASTER BILL OF MATERIALS (BOM) & COST SCHEDULE
Client: 2-Acre Moringa Commercial Orchard ¦ Standard: IS 12786 / IS 4985 ¦ Date: October 2026
Item # | Category | Item Description & Specification | Unit | Ordered Qty | Planned Usage | Spare Qty | Unit Rate (INR) | Total Amount (INR) | Application / Location
1 | PVC Pipes | 2" (63mm) PVC Pipe Class 2 (6 kg/cm2, 20ft length) | Length | 45 | 37 | 8 | 420 | 18900 | Zone 1 Mainline network (730 ft used)
2 | PVC Fittings | 2" PVC 90° Elbow | Nos | 30 | 18 | 12 | 45 | 1350 | Mainline routing & riser manifold bends
3 | PVC Fittings | 2" PVC Equal Tee | Nos | 30 | 12 | 18 | 55 | 1650 | Borewell, Corner, Tee A, Tee B & 8 Risers
4 | PVC Fittings | 2" PVC Collar / Coupler | Nos | 10 | 6 | 4 | 30 | 300 | Pipe length joins in trenches
5 | PVC Fittings | 2" PVC End Cap | Nos | 10 | 6 | 4 | 35 | 350 | Stubs (Borewell S, Corner E, Tee B W) & mainline ends
6 | PVC Fittings | 2" PVC Gate Valve (Header) | Nos | 10 | 2 | 8 | 350 | 3500 | Borewell delivery & field isolation
7 | PVC Pipes | 1.5" (50mm) PVC Pipe Class 2 (20ft length) | Length | 10 | 8 | 2 | 310 | 3100 | Plot A sublines & vertical riser drops (152 ft)
8 | PVC Fittings | 1.5" PVC 90° Elbow | Nos | 40 | 16 | 24 | 32 | 1280 | Plot A 4 overhead risers (4 per station)
9 | PVC Fittings | 1.5" PVC Equal Tee | Nos | 50 | 8 | 42 | 38 | 1900 | Plot A subline branch junctions
10 | PVC Fittings | 1.5" PVC Collar | Nos | 5 | 4 | 1 | 22 | 110 | Plot A subline joins
11 | PVC Pipes | 1.25" (40mm) PVC Pipe Class 2 (20ft length) | Length | 15 | 14 | 1 | 240 | 3600 | Plot B sublines & vertical riser drops (288 ft)
12 | PVC Fittings | 1.25" PVC 90° Elbow | Nos | 30 | 16 | 14 | 25 | 750 | Plot B 4 overhead risers (4 per station)
13 | PVC Fittings | 1.25" PVC Equal Tee | Nos | 40 | 8 | 32 | 30 | 1200 | Plot B subline branch junctions
14 | PVC Fittings | 1.25" PVC Collar | Nos | 5 | 4 | 1 | 18 | 90 | Plot B subline joins
15 | Consumables | PVC Solvent Cement (Heavy Duty 3L: 2L in 1/2L + 1L in 1/4L) | Liters | 3 | 2.5 | 0.5 | 480 | 1440 | All solvent-welded joints across 2 acres
16 | Consumables | Teflon Thread Seal Tape (12mm x 10m roll) | Nos | 5 | 4 | 1 | 20 | 100 | Threaded filter, gauge & valve connections
17 | Consumables | Hacksaw Blades (Bi-metal 12") | Nos | 4 | 4 | 0 | 25 | 100 | Field cutting of PVC pipes & laterals
18 | Drip Invoice #1 | 16mm Plain Lateral Pipe | Mtrs | 2000 | 1610 | 390 | 7.25 | 14500 | Plot B (32 rows x 165 ft) — 390m reserve
19 | Drip Invoice #2 | Tunning Dripper (P) (Adjustable 0-70 LPH) | Nos | 800 | 768 | 32 | 4 | 3200 | Plot B (24 drippers/row x 32 rows = 768)
20 | Drip Invoice #3 | Punching Tool (3mm precision punch) | Nos | 5 | 5 | 0 | 10 | 50 | Field crew tools for punching dripper holes
21 | Drip Invoice #4 | 16mm Endcap (Figure-8 / End plug) | Nos | 110 | 80 | 30 | 2 | 220 | 48 in Plot A + 32 in Plot B (30 spares)
22 | Drip Invoice #5 | 16mm Lateral Connector (Straight joiner) | Nos | 40 | 10 | 30 | 2 | 80 | Lateral line repair and emergency joining
23 | Drip Invoice #6 | 40x16x1Way TF Coller (Take-off collar West) | Nos | 35 | 32 | 3 | 25 | 875 | Plot B row connections into 40mm subline
24 | Drip Invoice #7 | 40mm Flush Valve | Nos | 8 | 8 | 0 | 30 | 240 | Plot B subline terminal flush points (8 arms)
25 | Drip Invoice #8 | 16x4x40 Inline Pipe (4 LPH @ 40cm drippers) | Mtrs | 3000 | 2926 | 74 | 5.5 | 16500 | Plot A (24 trenches x 390 ft) — 74m reserve
26 | Drip Invoice #9 | 50x16x2 Way Take of Coller (V-connector) | Nos | 25 | 24 | 1 | 30 | 750 | Plot A trench connections (East & West)
27 | Drip Invoice #10 | 50mm Flash Valve (Flush Valve) | Nos | 8 | 8 | 0 | 40 | 320 | Plot A subline terminal flush points (8 arms)
28 | Drip Invoice #11 | 2" Filter 'T' Type (Disc/Screen Filter) | Nos | 1 | 1 | 0 | 2750 | 2750 | Zone 1 Solar Borewell head filtration unit
29 | Drip Invoice #12 | 40mm Plain Ball Valve (1.25" control valve) | Nos | 8 | 8 | 0 | 130 | 1040 | Plot B overhead risers (2 per station x 4)
30 | Drip Invoice #13 | 50mm Plain Ball Valve (1.5" control valve) | Nos | 8 | 8 | 0 | 210 | 1680 | Plot A overhead risers (2 per station x 4)
|  | SUBTOTAL: PVC PIPES, FITTINGS & CONSUMABLES | [5 empty] | 39720 | 17 PVC Inventory Line Items
|  | SUBTOTAL: DRIP IRRIGATION INVOICE ITEMS | [5 empty] | 42205 | 13 Drip Commercial Invoice Line Items
|  | TOTAL MATERIAL COST (BEFORE TAX) | [5 empty] | 81925 | Ex-Factory Material Total
|  | CGST (9%) | [5 empty] | 7373.25 | Central Goods and Services Tax
|  | SGST (9%) | [5 empty] | 7373.25 | State Goods and Services Tax
|  | GRAND TOTAL PROJECT MATERIAL INVOICE | [5 empty] | 96671.5 | Full Project Procurement Value (INR)

## Zone_Allocation
ZONE-WISE MATERIAL & HYDRAULIC ALLOCATION MATRIX
Detailed breakdown of pipe footage, fittings, and tree counts per hydraulic zone
Zone ID | Zone Name & Crop | Target Area | Mainline Feed | Riser Stations | Subline Size & Run | Laterals & Emitters | Plant Count | Allocated Valves & Fittings
Zone 1 | Solar Borewell & Mainline Network | Infrastructure | 2" Class 2 (730 ft) | N/A (Header) | None | None | 0 | 1x 2" Filter 'T', 2x 2" Gate Valves, 1x 2" NRV, 4x 2" Tees, 4x 2" End Caps
Zone 2 | Plot A: East Field (PKM-1 Moringa) | 1.0 Acre (390x130 ft) | 2" Center (145 ft) | 4 Overhead (A1-A4 @ 30' spacing) | 1.5" (50mm) x 120 ft total | 16x4x40 Inline (2,926m across 24 trenches) | 3000 | 8x 50mm Ball Valves, 8x 50mm Flush Valves, 24x 50x16x2-Way Collars, 48x 16mm Caps
Zone 3 | Plot B: West Field (Bhagya Moringa) | 1.0 Acre (165x260 ft) | 2" Boundary (240 ft) | 4 Overhead (B1-B4 @ 64' spacing) | 1.25" (40mm) x 256 ft total | 16mm Plain (1,610m across 32 rows) | 750 | 8x 40mm Ball Valves, 8x 40mm Flush Valves, 32x 40x16x1-Way Collars, 768 Drippers, 32x Caps
TOTALS | 2-Acre Moringa Commercial Farm | 2.0 Acres | 1,115 ft Total Mainline | 8 Riser Stations | 376 ft Buried Sublines | 4,536m Drip Laterals Installed | 3750 | 16 Ball Valves, 16 Flush Valves, 56 Collars, 80 Caps, 768 Drippers

## Riser_and_Trench_Schedule
FIELD EXECUTION SCHEDULE: RISER TAPE MEASURES & PIPE CUT-LIST
Exact field dimensions from reference origins for excavation, plumbing, and riser assembly
Station Code | Reference Origin | Tape Measure Offset (ft) | Global CAD (X, Y) | Zone / Subline Arm | Trench / Row Spacing | Covered Range (Y) | Pipe Cut Lengths Required
Tee A | Plot A Center Entry | 0 | (500, 100) | Plot A Center Mainline Start | Mainline Entry | Y = 100 | 215 ft West from Tee B; 90 ft East from Corner
Riser A1 | Tee A (500, 100) | 30 | (500, 130) | Plot A Arms 1 & 2 | 5 ft Trench Spacing | Y = 115 to 145 | 1x 4ft 2" Riser; 2x 4ft 1.5" Drops; 2x 15ft 1.5" Sublines
Riser A2 | Tee A (500, 100) | 60 | (500, 160) | Plot A Arms 3 & 4 | 5 ft Trench Spacing | Y = 145 to 175 | 1x 4ft 2" Riser; 2x 4ft 1.5" Drops; 2x 15ft 1.5" Sublines
Riser A3 | Tee A (500, 100) | 90 | (500, 190) | Plot A Arms 5 & 6 | 5 ft Trench Spacing | Y = 175 to 205 | 1x 4ft 2" Riser; 2x 4ft 1.5" Drops; 2x 15ft 1.5" Sublines
Riser A4 | Tee A (500, 100) | 120 | (500, 220) | Plot A Arms 7 & 8 | 5 ft Trench Spacing | Y = 205 to 235 | 1x 4ft 2" Riser; 2x 4ft 1.5" Drops; 2x 15ft 1.5" Sublines
End Cap A | Tee A (500, 100) | 145 | (500, 245) | Plot A Mainline Terminal | Terminal End | Y = 245 | 1x 2" End Cap on 25ft mainline tail past Riser A4
Tee B | Plot B Entry Corner | 0 | (285, 100) | Plot B East Boundary Start | Mainline Entry | Y = 100 | Connected to Tee A via 215 ft 2" pipe
Riser B1 | Tee B (285, 100) | 24 | (285, 124) | Plot B Arms 1 & 2 | 8 ft Row Spacing | Y = 92 to 156 | 1x 4ft 2" Riser; 2x 4ft 1.25" Drops; 2x 32ft 1.25" Sublines
Riser B2 | Tee B (285, 100) | 88 | (285, 188) | Plot B Arms 3 & 4 | 8 ft Row Spacing | Y = 156 to 220 | 1x 4ft 2" Riser; 2x 4ft 1.25" Drops; 2x 32ft 1.25" Sublines
Riser B3 | Tee B (285, 100) | 152 | (285, 252) | Plot B Arms 5 & 6 | 8 ft Row Spacing | Y = 220 to 284 | 1x 4ft 2" Riser; 2x 4ft 1.25" Drops; 2x 32ft 1.25" Sublines
Riser B4 | Tee B (285, 100) | 216 | (285, 316) | Plot B Arms 7 & 8 | 8 ft Row Spacing | Y = 284 to 348 | 1x 4ft 2" Riser; 2x 4ft 1.25" Drops; 2x 32ft 1.25" Sublines
End Cap B | Tee B (285, 100) | 240 | (285, 340) | Plot B Mainline Terminal | Terminal End | Y = 340 | 1x 2" End Cap on 24ft mainline tail past Riser B4